## Roadmap
Commercial Systems Roadmap H2 2026 - merged backlog (Kev, Sille, Jonas)
Sources: Customer Systems Backlog H2 2026; Roadmap vs Capacity; H2 Planning meeting 27 May 2026. Built 5 Jun 2026.
ID | Initiative | Driver | Resource ask | FTE-q ask | Requested timing | Planned slot | Planned FTE | Status | Dependencies | Notes
CS-26H2-25 | Data Deduplication Implementation | Sille | SF Core (Nataša lead, Miranda, Pawel assist) | 2.5 | Q3 2026 | Sept-Oct 2026 (may slip to Nov) | SF Core committed | SF Core commitment 1 of 3 | Pre: -11 ARM. Oct absences may push completion | One of SF Core's 3 committed deliverables. ARM is prerequisite. Oct has known absences affecting Dedupe; may push to Nov. Unblocks Customer360, My Account, Preference Centre, Email-to-Case in 2027.
CS-26H2-01 | B2B partner data ownership to Salesforce | Sille / Jonas | SF Core (scoping) + Backend 2 | 1.5 (scoping) | Q3-Q4 2026 | H2: SCOPING only (~1.5 FTE-mo); impl 2027 | Pawel Q4 slack | Negotiable - SteerCo decides | Pre: -25 Dedup. Post: -20 Commission. Needs PG to engage | SF Core position: scoping in H2 only, implementation 2027. Only SteerCo 'Data & Systems' component that sits with SF Core. Lands in Pawel's Q4 slack if PG engages.
CS-26H2-09 | Lighthouse Phase 2 | Sille | SF Core (Miranda+Nataša+Arthur) | 2.5 | Q3-Q4 2026 | Q3 light ramp (scoping) + Q4 full | SF Core committed | SF Core commitment 1 of 3 | Sales/Service + CX scope brief; IVR/Connect transcripts; Aug AI hackathon | One of SF Core's 3 committed deliverables. Scope undefined (AI entry point, next best action, case dispositions, call summaries, web context). Phase 2 build ramps Sept as Arthur returns. What lands H2 vs 2027 is the discussion.
CS-26-H2-30 | My Account (SF user identification & mgmt) | Sille | SF Core 2-3, Backend 1 | 2-3 | Q3-Q4 2026 (pinned) | SF Core says Q1-Q2 2027 | - | CONFLICT: pinned Q3 vs SF Core 2027 | Pre: -25 Dedup must complete first | CONFLICT to resolve. Sverre pinned Q3; SF Core says realistic only 2027 (needs Dedupe done first). Digital Products owns customer-facing side. Activation was already late Sep/early Oct to avoid Lighthouse collision.
CS-26H2-06 | New payment methods (Apple Pay, Google Pay, Vipps) | Jonas | Backend 1 | 1.0 | Q3 2026 | Q3 2026 | 1.0 (BE) | Committed Q3 | Treasury approval; Commercial prioritisation | 'More or less ready to go' - test environment setup and accounts.
CS-26-H2-23 | Commercial platform (security + backups subset first) | Jonas | Platform 1, Backend 1 | 2.0 | Q3-Q4 2026 | Q3 2026 (subset) | 1.0 (Platform) | Committed Q3 | - | Off-site backups, env refresh automation, Linux support, Seaware load testing (feeds -24).
CS-26-H2-28 | BaU Q3 2026 | All (SF/SFMC/DC) | 20% reserve | ~1.0 | Q3 2026 | Q3 2026 | 20% | Committed Q3 | - | Protected reserve; intake discipline required.
CS-26H2-07 | Marketing Consent Preference model incl Double Opt-In | Kev | CRM/SFMC + SF Core commitment | 1.5 | Q3-Q4 2026 | CONFLICT: Kev Nov-Dec vs SF Core 2027 | Kev 1/mo Nov-Dec | CONFLICT: timing & ownership | Pre for -10; needs consent data clean-up first | CONFLICT. Kev plans Nov-Dec (needs SF Core commitment); SF Core says 2027, CX/Business owned. Depends on consent data clean-up. Kev P1: 'massive change - cannot be underestimated'.
CS-26-H2-26 | Incident Management for IROPS (finish) | Sille | SF Core 1 | 0.5 | Q3 2026 | Pawel Q4 slack (negotiable) | ~0.5 FTE-mo | Negotiable - SF Core call | - | ~80% complete, paused by Lighthouse. Small close-out; could land in Pawel's Q4 slack.
CS-26-H2-24 | Seaware production to OCI | Jonas | Backend 3, Platform 1 | 3.0 | Q3 2026 | Q4 2026 | 3.0 (BE+Pl) | Committed Q4 | Load testing in stage (via -23) before cutover | Go-live burst: 3-4 backend + dev team for cutover window. 'Low hanging fruit, almost done'.
CS-26-H2-29 | BaU Q4 2026 | All (SF/SFMC/DC) | 20% reserve | ~1.0 | Q4 2026 | Q4 2026 | 20% | Committed Q4 | - | Protected reserve.
CS-26-H2-11 | PG SF Person Account Integration (ARM) | Sille | SF Core (Pawel lead, Miranda) | 2.5 | Q1-Q3 2026 | Jul-Sept 2026 (SF Core) | SF Core committed | SF Core commitment 1 of 3 | PG-side delivery Aug-Sept (HIGH); any PG slip cascades | One of SF Core's 3 committed deliverables. Prerequisite (gate) for Dedupe. Critical path: ARM>Dedupe>2027 unlocks. NOTE: Kev's sheet also shows ARM Aug-Oct on CRM/DC team - clarify ownership/overlap.
CS-26-H2-10 | Preference Centre on Email / Web | Kev | CRM/SFMC + SF Core | 1.0 | Q3-Q4 2026 | CONFLICT: Kev Nov-Dec vs SF Core 2027 | Kev 1/mo Nov-Dec | CONFLICT: timing & sponsorship | Pre: -07 Consent (which needs data clean-up); sponsorship not confirmed | CONFLICT. Kev plans Nov-Dec; SF Core says 2027, CX/SFMC. Sponsorship (Michelle/Jenny) not confirmed.
CS-26H2-08 | Lighthouse: Agentforce Quality Management pilot | Sille | SF Core 2, QA 1 | 2.0 | Q3 2026 | Q1 2027 | 2.0 (SF) | Deferred to Q1 27 | Call transcripts from Amazon Connect in SF | Decision-shaped pilot incl. go/no-go for scale-up; post-Lighthouse capacity.
CS-26-H2-13 | Salesforce Comms Triggers (CCE) | Kev | SF 1-2, SFMC 1, CX 1 | 1.5 | Q3 2026 | Q1 2027 | 1.5 (SF) | Deferred to Q1 27 | CX strategy and activation | CCE wired after consent substrate.
CS-26-H2-27 | Email-to-Case | Sille | SF Core 1-2, Business 1-2 | 1-2 | Q3 2026 | Q1-Q2 2027 (SF Core position) | - | Deferred to 2027 | Pre: -25 Dedupe complete; needs business resource (1-2 FTE) | SF Core: sequence after Dedupe, needs business/IT-OT resource alongside SF. 2027.
CS-26-H2-22 | Partner API v2 | Jonas | Backend 2 | 4.0 | Q3-Q4 2026 | Q1 27 (build) + Q2 27 (deprecation/migration) | 2.0 + 1.0 (BE) | Re-phased across year | May need SF work for API signup automation | Jyhe dedicated rest of year + Lasse >=50%. Only backend item 'set in stone'. v1 sunset target moves with re-phasing.
CS-26-H2-21 | Bynder integration (Partner API) | Jonas / Kev | Backend 1, SFMC 1, B2X 1 | 1.0 | Q3 2026 | Q1 2027 | 1.0 (BE) | Deferred to Q1 27 | Contentful updated with Bynder links | Small task per Jonas (Lasse). Levelled to Q1 27 for capacity.
CS-26-H2-17 | CRM Segmentation Support | Kev | CRM/DC team (Kev) | 2.0 | Q3-Q4 2026 | Jul-Dec 2026 (CRM team) | 1.0->0.25/mo (CRM) | CRM-planned H2 (reconciled) | CX strategies and briefs; same scarce DC resource as Agentforce | Capacity page deferred to Q2 27 as one SF pool; Kev carries it on CRM/DC team Jul-Dec. Pulls the Data Engineer gap.
CS-26-H2-14 | Salesforce Data Support (mobile cleansing, DACH bug) | Kev | SF 1, SFMC 1 | 1.0 | Q4 2026 | Q2 2027 | 1.0 (SF) | Deferred to Q2 27 | - | Levelled for capacity.
CS-26-H2-12 | AirPort Express Automation B2B (Flytoget) | Kev | SF 1, SFMC 2 | 1.0 | Q4 2026 | Q2 2027 | 1.0 (SF) | Deferred to Q2 27 | - | Levelled for capacity.
CS-26-H2-20 | Commission on Tour elements | Jonas | Backend 2 | 2.0 | 2026 (scope TBD) | Q2 2027 | 2.0 (BE) | Deferred to Q2 27 | Pre: -01 partner data | Biggest external-stakeholder ask. Cathrine/Per Martin/Astrid must be told this quarter. Scoping workshop early H2 (per Jonas).
CS-26H2-05 | SFS / Fidelio stabilisation (investigation) | Jonas | Backend 2, Automation 1 | 3.0 | Q3 2026 | Q2 2027 (investigation start) | 1.5 (BE+DC) | Deferred to Q2 27 | Discovery may pull in Salesforce | Needs dedicated investigation, not firefighting. Lowest cost-of-delay; no external pin.
CS-26-H2-16 | Review Platform Integration (Trustpilot) | Kev | CRM/DC team (Kev) | 2.0 | Q3 2026 | Jul-Nov 2026 (CRM team) | 0.5/mo (CRM) | CRM-planned H2 (reconciled) | Platform decision; Michelle to ratify timeline | Capacity page descoped it as one SF pool; Kev carries it on the CRM/DC sub-team. Stays IN. SF Core / Data Cloud integration hooks still need confirming.
CS-26-H2-18 | Travel Docs - Phase 1 (DocForge into SFMC/Web) | Kev / Jonas | CRM team (Kev) + Backend 1 | 2.0 | Q3 2026 | Jul-Oct 2026 (CRM) - backend gated | 1.0->0.5/mo (CRM) | CRM-planned H2; backend is the gate | CX designs/resources; DocForge POC-to-Service (Backend) | CRM-side fits Kev's plan. Constraint is Backend (Jonas) + DocForge service path, which capacity plan put at 27H2. Decide backend slot.
CS-26H2-03 | Agent-portal for top CSC flows | Jonas | Backend 1, B2X Frontend 1 | 2.0 | Q3 2026 | UNRESOLVED - no slot in capacity plan | - | Unresolved - needs decision | Opens shared REST API surface to B2X and SF; BDA removal goal | Backend FTE not allocated in quarterly plan. Either slot explicitly (displaces ~1 BE FTE-q) or defer.
CS-26H2-04 | Automate loading and IROPS tasks | Jonas | Backend 1 | 1.0 | Q3 2026 | UNRESOLVED - no slot in capacity plan | - | Unresolved - needs decision | Process owners define automation rules | Candidate to absorb into Backend ops/automation envelope or defer; decide explicitly.
CS-26-H2-15 | CSC Sales & Groups Live Reporting | Kev | SF 1-2, Data Cloud 1 | 1.5 | Q3 2026 | UNRESOLVED - no slot in capacity plan | - | Unresolved - needs decision | NO S&S team adoption | SF has zero Q3 headroom; earliest realistic slot Q1 27 unless something else moves.

## FTE Loading (KW view)
Planned FTE loading vs capacity (FTE-quarters) - KW top-down alignment scenario
NOTE: one balancing scenario. Superseded in places by the bottom-up team positions (see SF Core, CRM Team, Conflicts tabs). SF here = combined pool; in reality SF Core (Sille) and CRM (Kev) are separate teams.
Stream | Capacity/q | Q3 2026 | Q4 2026 | Q1 2027 | Q2 2027
SF | 5.5 | 5.5 | 5.75 | 5.5 | 4.5
Backend | 2.5 | 1 | 2 | 3 | 4.5
Platform | 1 | 1 | 1 | 0 | 0
Total planned | 9 | 7.5 | 8.75 | 8.5 | 9
Headroom vs 9.0 |  | 1.5 | 0.25 | 0.5 | 0
Allocation detail
Initiative | Stream | Quarter | FTE
CS-26H2-25 Dedup | SF | Q3 2026 | 2
CS-26H2-01 Partner data (scope+model) | SF | Q3 2026 | 1
CS-26H2-09 Lighthouse Ph2 (trimmed) | SF | Q3 2026 | 1.25
CS-26-H2-30 My Account Ph1 | SF | Q3 2026 | 1.25
CS-26H2-06 New payment methods | Backend | Q3 2026 | 1
CS-26-H2-23 Commercial platform (subset) | Platform | Q3 2026 | 1
CS-26H2-01 Partner data (implementation) | SF | Q4 2026 | 2.5
CS-26-H2-30 My Account Ph2 | SF | Q4 2026 | 1.25
CS-26H2-07 Marketing Consent backend | SF | Q4 2026 | 1.5
CS-26-H2-26 IROPS Incident Mgmt (finish) | SF | Q4 2026 | 0.5
CS-26-H2-24 Seaware to OCI | Backend | Q4 2026 | 2
CS-26-H2-24 Seaware to OCI | Platform | Q4 2026 | 1
CS-26-H2-10 Preference Centre | SF | Q1 2027 | 1
CS-26H2-08 Agentforce QM pilot | SF | Q1 2027 | 2
CS-26-H2-13 SF Comms Triggers | SF | Q1 2027 | 1.5
CS-26-H2-27 Email-to-Case (start) | SF | Q1 2027 | 1
CS-26-H2-22 Partner API v2 (build) | Backend | Q1 2027 | 2
CS-26-H2-21 Bynder integration | Backend | Q1 2027 | 1
CS-26-H2-17 CRM Segmentation | SF | Q2 2027 | 1.5
CS-26-H2-14 SF Data Support | SF | Q2 2027 | 1
CS-26-H2-12 AirPort Express B2B | SF | Q2 2027 | 1
CS-26-H2-27 Email-to-Case (finish) | SF | Q2 2027 | 0.5
CS-26-H2-11 ARM Phase 2 tail | SF | Q2 2027 | 0.5
CS-26-H2-22 Partner API v2 (deprecation) | Backend | Q2 2027 | 1
CS-26-H2-20 Commission on Tour elements | Backend | Q2 2027 | 2
CS-26H2-05 SFS/Fidelio investigation | Backend | Q2 2027 | 1.5

## Capacity & Constraints
Capacity baseline (per quarter)
Stream | Bodies | Ops draw | BaU reserve | Project capacity / quarter
Salesforce (Kev + Sille pools) | 8.0 | 2.5 total (Hanif Ops-only + 1.5 across bodies) | ~1.0 (20%) | 5.5 FTE
Backend + Platform (Kato chapter + Jonas) | 7.0 (Ove 50%, Jonas 0.5 IC) | 3.0 | maintenance buffer | 4.0 FTE (~3.5 after buffer)
Combined | 15.0 | 4.5 + Hanif | ~1.0 | ~9 FTE per quarter
Availability constraints (from Sverre 2026-05-26 + H2 planning meeting):
- Serhii Volynets, Rasmus Mohr, Anders Harbo unavailable Q3/Q4 2026
- Hanif = Ops only; Kirill Harjo = QA, 100% allocated; Alexander Rostum & Kato Klaeboe manager-only
- Kev's project pool = Kev + Ismail Ferullo + Guljar Shaikh; ~25% on BAU/ops support; vacation coverage needed over next six months
- Sille's pool = Sille + Arthur + Miranda + Natasa + Pawel; Jul-Aug effective 1.8 FTE, Sep onwards 2.4 FTE; 20% BAU + 20% on-call; no slack for sickness
- Pawel sole resource on ARM until ~Aug; Miranda needed at the finish line
- Backend: Jyhe dedicated to Partner API rest of year, Lasse >=50% + Bynder; 'nothing set in stone except Partner API'
- Seaware OCI go-live needs burst of 3-4 backend + dev team for cutover window (Q4)
- Espen on security roadmap (tasks TBD); unknown compliance requirements may land

## CRM Team (Kev) Monthly
CRM / SFMC / Data Cloud team - monthly plan (Kev Gaisford)
Team = Kev + Guljar + Ismail (3 people). Source: Kev resourcing view, 6 Jun 2026. ** excludes vacation.
Initiative | July | August | Sept | Oct | Nov | Dec
Travel Docs | 1 | 1 | 0.5 | 0.5
CRM Segmentation | 1 | 0.5 | 0.5 | 0.25 | 0.25 | 0.25
Compass CRM Reporting | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
TrustPilot | 0.5 | 1 | 0.5 | 0.5 | 0.5
AirPort Express B2B | [5 empty] | 0.25
Voice of Customer | 0.5 | 0.5 | 0.5
ARM |  | 0.25 | 1 | 1
Dedupe |  |  |  | 1 | 1
Consent Management* |  |  |  |  | 1 | 1
Preference Center* |  |  |  |  | 1 | 1
Support / Ops | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Total planned | 3.75 | 4 | 3.75 | 4 | 4.5 | 3.25
* Need commitment from SF Core (Consent before Preference Center)
** Does not include vacation
NOT PLANNED - no CRM capacity (needs SF Core / other team or descope)
Initiative | July | August | Sept | Oct | Nov | Dec
Lighthouse 2 | 1 | 1 | 1 | 1 | 1 | 1
B2B Data Ownership downstream |  | 1 | 1 | 0.5 | 0.5
Commercial NorthStar - Groups Ops Report | 0.5 | 0.5
Brochure Fulfillment Automation |  |  | 0.5
Kev's headline: 'In a word, no.' Team needs a dedicated Data Engineer. CRM Segmentation + Agentforce pull the same scarce resource.
Gap is being plugged by Kev building solutions himself, displacing the Product Owner role (direction, prioritisation, stakeholder management).

## SF Core (Sille) Position
SF Core H2 2026 - Position (Sille Antonsen)
Team = Pawel, Nataša, Miranda, Arthur (4 delivery FTE) + Sille as Project Owner on top. SEPARATE pool from Kev's CRM team.
Capacity (best case, before holidays + TOIL)
| Jul-Aug | Sept-Dec | Notes
Delivery team (nominal) | 3.0 | 4.0 | Arthur out for summer holiday Jul-Aug
Minus BaU (20%) | -0.6 | -0.8 | Rotated, non-negotiable floor
Minus On Call (20%) | -0.6 | -0.8 | Daily coverage incl. weekends (Lighthouse/Omni consequence)
Available for project work | 1.8 | 2.4 | ~13 FTE-months across H2
The three committed deliverables
ID | Initiative | When | Team | Why critical
H2-11 | ARM (Person Account integration) | Jul-Sept | Pawel lead, Miranda | Prerequisite (gate) for Dedupe; PG dependency; already in flight
H2-25 | Dedupe (SF master for person data) | Sept-Oct | Nataša + Miranda, Pawel assist | Unblocks Customer360, My Account, Pref Centre, Email-to-Case in 2027. Oct absences may push to Nov
H2-09 | Lighthouse Phase 2 | Q3 light ramp + Q4 full | Miranda lead, Nataša + Arthur | Scope undefined; ramps Sept as Arthur returns; what lands H2 vs 2027 is the discussion
Critical path: ARM (Jul-Sept) > Dedupe (Sept-Oct, ARM prerequisite) > downstream unlocks 2027. Miranda is the Sept crunch pivot (on all three).
Up for discussion - depends on value from SteerCo (could land in Pawel's Q4 slack, or push the three out)
ID | Item | Position | Rough size | Who decides
H2-26 | IROPS Incident Mgmt (finish) | ~80% done, paused by Lighthouse; small close-out | ~0.5 FTE-mo | SF Core call
H2-01 | B2B Data Ownership (scoping) | Scoping in H2 only; impl 2027; if PG engages | ~1.5 FTE-mo | SteerCo
H2-30 | My Account | Wants Dedupe done first; realistic only 2027 | 2-3 FTE | Digital Products
H2-27 | Email-to-Case | Needs business resource; after Dedupe; 2027 | 1-2 FTE | IT/OT + business
H2-10 | Preference Center | Depends on H2-07; sponsorship not confirmed; 2027 | 1 FTE | CX / SFMC
H2-07 | Marketing Consent + Opt-In | Depends on consent data clean-up; gates H2-10 | TBD | CX / Business
Open risks (SF Core wants surfaced at prioritisation):
- Capacity vs SteerCo expectation (HIGH): SteerCo 'Data & Systems' assumes nominal headcount; real project capacity is 2.4 FTE. Of VAT/Commission/B2B, only H2-01 sits with SF Core (scoping only).
- Miranda's September crunch (HIGH): ARM close + Dedupe start + Phase 2 ramp all converge on Miranda. Sequencing risk; backup needed.
- ARM PG dependency (HIGH): one named SF resource (Pawel) + PG-side delivery Aug-Sept. Any PG slip cascades into Dedupe and the whole critical path.
- Holidays + TOIL not in the 2.4 number (MED): Oct absences hit Dedupe; Phase 1 TOIL not drawn down.
- Phase 2 scope undefined (MED): without a scoped brief from Sales/Service + CX, Phase 2 ramps into open work.
- On Call not formally established (MED): without a Norwegian vakttjeneste rota, incidents eat project capacity reactively.
- Go-lives cannot be stacked: ARM and Dedupe go-lives cannot share a weekend; hypercare eats 2-4 weeks per release on top of On Call.

## Conflicts & Decisions
Cross-team conflicts & decisions for SteerCo / prioritisation
Where the three team positions (Kev, Sille, Jonas) and the KW alignment view disagree. Each needs an explicit decision.
# | Decision | Positions in tension | Recommended resolution | Owner
1 | My Account (-30) timing | Sverre pinned Q3/Q4 2026; SF Core says realistic only 2027 (needs Dedupe done first, which completes Oct/Nov) | Accept 2027 for SF identity work; let Digital Products run the customer-facing build in parallel where it doesn't need the SF person model. Unpin Q3. | Sverre + Sille + Digital Products
2 | Consent (-07) & Preference Centre (-10) | Kev plans Nov-Dec on CRM/SFMC (needs SF Core commitment); SF Core says 2027 and CX/SFMC-owned; sponsorship (Michelle/Jenny) not confirmed | Confirm sponsorship + consent data clean-up first. If sponsored, Kev runs CRM-side Nov-Dec but the SF Core dependency must be explicitly resourced - SF Core has no H2 slot for it. | Sverre + Kev + Sille + CX
3 | ARM (-11) ownership / overlap | SF Core (Sille): Pawel + Miranda, Jul-Sept. Kev's sheet also shows ARM Aug-Oct on CRM/DC team | Clarify single owner. ARM = SF Core (Pawel) per Sille; Kev's line is likely DC integration assist - confirm and de-duplicate the FTE. | Sille + Kev
4 | TrustPilot (-16), Travel Docs (-18), Segmentation (-17) | KW alignment view descoped/deferred these (treated SF as one pool); Kev plans all three on CRM team in H2 | Keep IN H2 on Kev's CRM/DC team. Travel Docs still gated by Backend (Jonas) + DocForge service path - decide backend slot separately. | Kev + Jonas
5 | SteerCo 'Data & Systems' (VAT, Commission, B2B) capacity gap | SteerCo assumes SF Core absorbs more; real SF Core project capacity is 2.4 FTE and only B2B(-01) scoping sits with them. VAT(-19) + Commission(-20) are Backend | Re-baseline SteerCo expectation to 2.4 FTE. VAT lands Q3 (Backend); Commission(-20) slips to Q2 2027 (needs -01 + -19 first); B2B is scoping-only in H2. | Sverre at SteerCo
6 | Lighthouse Phase 2 (-09) scope | SF Core commits the team but scope undefined ('everything' demand); Kev's CRM team has ZERO capacity for it | Sales/Service + CX deliver a scoped, prioritised feature brief before Q3. Bound what lands H2 vs 2027. It is an SF Core-only delivery. | Sille + Jude (Sales/Service) + CX
7 | Backend unscheduled asks (-03 Agent-portal, -04 Loading/IROPS auto) | On Jonas's canvas but no slot in the balanced plan after Partner API + VAT + payments + Seaware + 30% ops | Slot -03 frontend on B2X now; decide backend API slot (displaces ~1 BE FTE-q or defers to Q1 27). Fold -04 into automation envelope or defer. | Sverre + Jonas + Kato
8 | CRM team -15 Live Reporting & capacity | Kev's 3-person team is fully loaded every month; -15 has no slot. Kev: 'In a word, no' - needs a dedicated Data Engineer | Approve a Data Engineer hire (CRM Segmentation + Agentforce compound the gap). Until then -15 has no realistic slot before Q1 2027; Kev's PO role is being displaced by hands-on delivery. | Sverre (headcount)