Commercial Systems Roadmap H2 2026

Merged from the Kev Gaisford (CRM/SFMC/Data Cloud), Sille Antonsen (SF Core) and Jonas Roineslien (Backend & Platform) roadmaps. Draft for SteerCo / prioritisation, 6 June 2026. Owner: Sverre Stornes.

# 1. Executive summary

The three driver roadmaps were merged into the 29-row Customer Systems Backlog H2 2026. A top-down capacity model (the KW alignment view) balanced that backlog into a Q3 2026 – Q2 2027 schedule. The two team leads have since returned their own bottom-up positions, which are authoritative and diverge from the top-down view in important places. This document carries both and surfaces the gaps as explicit decisions.

Two facts reframe the plan. First, there are two separate Salesforce teams, not one pool: SF Core (Sille — Pawel, Nataša, Miranda, Arthur) at 2.4 FTE for projects from September (1.8 over the summer), and CRM/SFMC/Data Cloud (Kev — Kev, Guljar, Ismail) which is fully loaded every month on its own list. Second, SF Core commits to only three deliverables in H2 — ARM, Dedupe and Lighthouse Phase 2 — and treats everything else as negotiable. Notably, SF Core says My Account is realistic only in 2027 (it needs Dedupe finished first), which directly contradicts the Q3 pin.

There are eight cross-team decisions for SteerCo (section 8). The headline ones: My Account timing (pinned Q3 vs SF Core 2027); Consent / Preference Centre (Kev plans Nov–Dec but SF Core says 2027 and sponsorship is unconfirmed); and the SteerCo capacity expectation — of the 'Data & Systems' trio (VAT, Commission, B2B), only B2B scoping sits with SF Core, against a real 2.4 FTE. Kev's bottom line on his team is 'in a word, no' without a dedicated Data Engineer.

# 2. Capacity baseline — three separate streams

| Stream | Team | Project capacity | Position |
| --- | --- | --- | --- |
| SF Core (Sille) | Pawel, Nataša, Miranda, Arthur (+Sille PO) | 1.8 FTE Jul–Aug; 2.4 from Sept | Three commitments only; rest negotiable |
| CRM/SFMC/DC (Kev) | Kev, Guljar, Ismail | ~4 FTE/mo, fully loaded | Own list fully booked; 'in a word, no' to more |
| Backend + Platform (Jonas) | Kato chapter + Jonas (0.5 IC) | ~3.5 FTE/q after 30% ops | Partner API locked; rest negotiable |

Constraints baked into the plan:

- SF Core — ARM (Jul–Sept, Pawel + Miranda) gates Dedupe (Sept–Oct, Nataša + Miranda). Lighthouse Phase 2 ramps from September as Arthur returns. BaU + On Call are a permanent 40% floor (On Call is the cost of Lighthouse/Omnichannel going live — daily coverage incl. weekends). 2.4 FTE is best-case before holidays and TOIL; October has known absences hitting Dedupe. Miranda is on all three in September — a sequencing risk.

- CRM — Three people, fully loaded every month (3.75–4.5). ~25% standing BAU/ops. Needs a dedicated Data Engineer — Segmentation and Agentforce pull the same scarce resource. Kev plugging the gap by building himself, displacing the Product Owner role.

- Backend — Jyhe dedicated to Partner API rest of year, Lasse ≥50% (+ Bynder). 'Nothing set in stone except Partner API.' Serhii, Rasmus and Anders Harbo unavailable Q3/Q4; Hanif Ops-only; Kirill 100% QA. 30% of weekly capacity is commercial-systems operations.

# 3. SF Core position (Sille)

SF Core commits to three deliverables in H2, run in parallel on a 2.4 FTE envelope. Everything else is explicitly negotiable, sized roughly, and only fits in Pawel's Q4 slack or by pushing one of the three out.

| ID | Commitment | When | Team | Why critical |
| --- | --- | --- | --- | --- |
| -11 | ARM (Person Account integration) | Jul–Sept | Pawel lead, Miranda | Gate for Dedupe; PG dependency; already in flight |
| -25 | Dedupe (SF master for person data) | Sept–Oct (may slip Nov) | Nataša + Miranda, Pawel assist | Unblocks My Account, Pref Centre, Email-to-Case in 2027 |
| -09 | Lighthouse Phase 2 | Q3 light ramp + Q4 full | Miranda lead, Nataša + Arthur | Ramps Sept as Arthur returns; scope undefined |

Negotiable (SteerCo value needed): -26 IROPS finish (~0.5 FTE-mo, Pawel Q4 slack); -01 B2B data — scoping only in H2 (~1.5 FTE-mo), implementation 2027; -30 My Account, -27 Email-to-Case, -10 Preference Centre, -07 Consent — all 2027 in SF Core's view. Critical path: ARM → Dedupe → 2027 unlocks. September is the crunch: ARM closing, Dedupe starting and Phase 2 ramping all land on Miranda (sequencing risk, backup needed).

# 4. CRM team position (Kev) — monthly

Kev's three-person team (Kev, Guljar, Ismail) is fully loaded every month at 3.75–4.5 FTE. This carries TrustPilot, Travel Docs and CRM Segmentation in H2 — the items the top-down view had descoped — on the CRM/Data Cloud team rather than SF Core. Figures are FTE/month.

| Initiative | Jul | Aug | Sep | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- |
| Travel Docs | 1 | 1 | 0.5 | 0.5 |  |  |
| CRM Segmentation | 1 | 0.5 | 0.5 | 0.25 | 0.25 | 0.25 |
| Compass CRM Reporting | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |
| TrustPilot | 0.5 | 1 | 0.5 | 0.5 | 0.5 |  |
| AirPort Express B2B |  |  |  |  |  | 0.25 |
| Voice of Customer | 0.5 | 0.5 | 0.5 |  |  |  |
| ARM (DC assist) |  | 0.25 | 1 | 1 |  |  |
| Dedupe (DC assist) |  |  |  | 1 | 1 |  |
| Consent Mgmt * |  |  |  |  | 1 | 1 |
| Preference Center * |  |  |  |  | 1 | 1 |
| Support / Ops | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |
| Total planned | 3.75 | 4 | 3.75 | 4 | 4.5 | 3.25 |

* Needs commitment from SF Core (Consent before Preference Centre) — see conflict 2. Excludes vacation.

Not planned — no CRM capacity (needs another team or descope): Lighthouse 2 (1 FTE/mo Jul–Dec — confirms it is SF Core-only); B2B Data Ownership downstream (Aug–Nov); Commercial NorthStar Groups Ops Report (Jul–Aug); Brochure Fulfilment Automation (Sep). Kev's bottom line: 'in a word, no' without a dedicated Data Engineer.

# 5. Backend & Platform position (Jonas)

Partner API is the only locked item (Jyhe dedicated rest of year, Lasse ≥50%); 30% of capacity is operations. Committed H2: VAT + invoice templates (-19, regulatory, MVP July), new payment methods (-06), Bynder (-21, small), Commercial platform / maintenance (-23) including Seaware load testing, and Seaware production to OCI (-24, go-live burst of 3–4 backend + dev team). Scope-dependent: Agent-portal (-03), Loading/IROPS automation (-04), SFS/Fidelio stabilisation (-05, investigation first), Commission on Tour (-20, scope undefined — workshop early H2, needs -19 and -01 first so realistically Q2 2027).

# 6. Consolidated schedule

Where the three positions agree, the cross-team plan is:

## Q3 2026 (Jul–Sep)

| Stream | Committed | Notes |
| --- | --- | --- |
| SF Core | -11 ARM (Jul–Sept), -25 Dedupe (Sept–Oct), -09 Lighthouse Ph2 (scoping/light ramp) | ARM gates Dedupe; Sept is Miranda's crunch |
| Backend | -19 VAT (MVP July), -06 payments, -23 platform subset (incl. Seaware load test) | VAT is regulatory; platform subset feeds Q4 OCI |
| CRM | Travel Docs, Segmentation, TrustPilot, Compass, Voice of Customer, Support | Team fully loaded Jul–Sep (3.75–4.0/mo) |
| All | -28 BaU (20% reserve) | Protected |

## Q4 2026 (Oct–Dec)

| Stream | Committed | Notes |
| --- | --- | --- |
| SF Core | -25 Dedupe finish, -09 Lighthouse Ph2 (full); negotiable: -26 IROPS, -01 B2B scoping in Pawel's Q4 slack | Oct absences may push Dedupe to Nov |
| Backend | -24 Seaware OCI cutover, Partner API continues | Cutover window kept clear |
| CRM | Segmentation tail, TrustPilot, AirPort Express (Dec), Consent + Pref Centre (CONFLICT), Support | Nov peak 4.5/mo; Consent/PrefCentre disputed (see conflict 2) |
| All | -29 BaU (20% reserve) | Protected |

## H1 2027 tail (deferred by team positions)

-30 My Account (needs Dedupe done — SF Core says 2027), -27 Email-to-Case (after Dedupe, needs business resource), -07 Consent / -10 Preference Centre (if not resolved into Q4), -08 Agentforce QM pilot, -13 SF Comms Triggers, -22 Partner API v2 build + deprecation, -20 Commission on Tour (after -19 and -01), -05 SFS/Fidelio investigation, -17 Segmentation overflow, -14 SF Data Support, -12 AirPort Express. Flag: Q2 2027 backend demand still exceeds the ~3.5 envelope — resolve -20 scope at the early-H2 workshop.

# 7. Conflicts & decisions for SteerCo

Eight points where the team positions or the top-down view disagree. Each needs an explicit decision; the highlighted column is the tension.

| # | Decision | Tension | Recommended resolution |
| --- | --- | --- | --- |
| 1 | My Account (-30) timing | Pinned Q3 vs SF Core says 2027 (needs Dedupe first) | Unpin Q3; accept 2027 for SF identity work; let Digital Products run customer-facing build in parallel where it doesn't need the SF person model |
| 2 | Consent (-07) & Preference Centre (-10) | Kev plans Nov–Dec (needs SF Core); SF Core says 2027 & CX-owned; sponsorship unconfirmed | Confirm sponsorship + consent data clean-up first. If sponsored, Kev runs CRM-side but the SF Core dependency must be explicitly resourced — SF Core has no H2 slot |
| 3 | ARM (-11) ownership / overlap | SF Core (Pawel, Jul–Sept) vs Kev's sheet shows ARM Aug–Oct on CRM/DC | Clarify single owner; Kev's line is likely DC integration assist — confirm and de-duplicate the FTE |
| 4 | TrustPilot, Travel Docs, Segmentation | Top-down view descoped/deferred; Kev plans all three in H2 | Keep IN on Kev's CRM/DC team; Travel Docs still gated by Backend + DocForge — decide that slot separately |
| 5 | SteerCo 'Data & Systems' capacity gap | SteerCo assumes SF Core absorbs more; real capacity 2.4 FTE; only B2B scoping sits with SF Core | Re-baseline to 2.4 FTE. VAT Q3 (Backend); Commission Q2 2027; B2B scoping-only in H2 |
| 6 | Lighthouse Phase 2 (-09) scope | SF Core commits the team but scope undefined ('everything'); CRM has zero capacity for it | Sales/Service + CX deliver a scoped, prioritised brief before Q3; bound H2 vs 2027; SF Core-only delivery |
| 7 | Backend unscheduled asks (-03, -04) | On Jonas's canvas but no slot after Partner API + VAT + payments + Seaware + 30% ops | Slot -03 frontend on B2X now; decide backend API slot (displaces ~1 BE FTE-q or defers); fold -04 into automation envelope or defer |
| 8 | CRM team capacity / -15 Live Reporting | 3-person team fully loaded; -15 has no slot; 'in a word, no' without a Data Engineer | Approve a Data Engineer hire; until then -15 has no slot before Q1 2027; Kev's PO role is being displaced by hands-on delivery |

# 8. Dependency chains

- -25 Dedup → -01 Partner data → -20 Commission (the person/partner data chain)

- -19 VAT → -20 Commission (commission engine on top of VAT-compliant invoicing)

- -07 Marketing Consent → -10 Preference Centre → downstream My Account preference surfaces and dynamic retargeting (E-commerce)

- -25 / -01 substrate → -27 Email-to-Case and -30 My Account (Customer 360 chain)

- -23 Seaware load testing → -24 OCI cutover; OCI opens B2X direct Sabre integration

- -11 ARM (completes ~Aug) is the read-model substrate for -01

- Cross-team: Digital Products' Excursions Self-Service and Add-ons assume Backend endpoints that are NOT budgeted in this plan; date-picker may reuse an existing Backend service. Treat as new demand intake, not assumptions.

# 9. Risks

- R1 — Miranda's September crunch (HIGH): ARM closing, Dedupe starting and Phase 2 ramping all converge on one person. Sequencing risk, not capacity — the handover week needs planning and a named backup.

- R2 — ARM → Dedupe critical path with PG dependency (HIGH): PG-side delivery Aug–Sept; any PG slip cascades through Dedupe and every 2027 unlock. One named SF resource (Pawel).

- R3 — SteerCo expectation vs real capacity (HIGH): the 'Data & Systems' narrative assumes nominal headcount; real SF Core project capacity is 2.4 FTE and only B2B scoping sits with them. Must be re-baselined before commitments are made.

- R4 — CRM team overload (HIGH): three people fully loaded; Segmentation + Agentforce pull the same scarce data-engineering resource; the gap is plugged by Kev building himself, displacing the Product Owner role. Mitigation: dedicated Data Engineer hire.

- R5 — -09 scope discipline (MED): without a scoped brief from Sales/Service + CX, Lighthouse Phase 2 ramps into open work and risks over-promising on AI features.

- R6 — Holidays + TOIL not modelled (MED): 2.4 FTE is best-case; October absences hit Dedupe directly; Phase 1 TOIL not yet drawn down.

- R7 — Go-lives cannot be stacked (MED): ARM and Dedupe go-lives cannot share a weekend; hypercare eats 2–4 weeks per release on top of On Call; CAB lead time applies.

- R8 — On Call not formally established (MED): without a Norwegian vakttjeneste rota, incidents eat project capacity reactively and the 20% allocation is invisible to planning.

# 10. Sources

- Customer Systems Backlog H2 2026 (Confluence CS space) — the merged Kev / Sille / Jonas backlog (29 rows)

- Roadmap vs Capacity / Capacity POC by KW (Confluence CS space) — top-down alignment model and gap analysis

- SF Core H2 2026 — Position (Sille Antonsen) — team capacity, three commitments, negotiables, risks

- CRM team monthly resourcing view (Kev Gaisford, 6 Jun 2026)

- Backend & Platform H2 canvas (Jonas Roineslien, 12 May 2026); Roadmap 2026 — Backend & Platform Services (Confluence PS space)

- H2 Planning Cross-Functional Roadmap Discussion, 27 May 2026 (Notion meeting note)