## Prioritised Roadmap
Customer Systems Roadmap H2 2026 — Prioritised
Three streams. P1 = committed, P2 = planned/at-risk, P3 = backlog (deferred / needs decision). Built 6 Jun 2026.
Stream | Priority | ID | Initiative | Horizon | Lead / team | FTE-q | Status | Dependency / note
SF Sales & Service Operations | P1 | H2-11 | ARM – PG↔SF Person Account integration | Q3 (Jul–Sep) | Pawel + Miranda | 2.5 | Committed | Gates Dedupe; PG-side delivery Aug–Sep
SF Sales & Service Operations | P1 | H2-25 | Dedupe – SF master for person data | Q3 (Sep–Oct, may slip Nov) | Nataša + Miranda, Pawel assist | 2.5 | Committed | Needs ARM; Oct absences
SF Sales & Service Operations | P1 | H2-09 | Lighthouse Phase 2 | Q3 scope → Q4 full | Miranda + Nataša + Arthur | 2.5 | Committed | Needs scoped CX / Sales&Service brief
SF Sales & Service Operations | P2 | H2-26 | IROPS Incident Mgmt – finish | Q4 (Pawel slack) | Pawel | 0.5 | Negotiable | ~80% done; paused by Lighthouse
SF Sales & Service Operations | P2 | H2-01 | B2B partner data ownership – scoping | Q4 (Pawel slack) | Pawel + PG | 1.5 | Negotiable · SteerCo | Needs PG engage; impl 2027
SF Sales & Service Operations | P3 | H2-30 | My Account – SF identity & user mgmt | 2027 | SF S&S | 2-3 | Deferred · CONFLICT (pinned Q3) | Needs Dedupe done first
SF Sales & Service Operations | P3 | H2-27 | Email-to-Case | 2027 | SF S&S + business | 1-2 | Deferred | Needs Dedupe + business resource
SF Sales & Service Operations | P3 | H2-08 | Agentforce Quality Mgmt pilot | 2027 | SF S&S + QA | 2.0 | Deferred | Connect transcripts in SF
SF Sales & Service Operations | P3 | M&D-135 | Case Statuses in My Account | 2027 | SF S&S | 1.0 | Deferred | SF capacity + Dedupe
SF Sales & Service Operations | P3 | H2-15 | CSC Sales & Groups live reporting | 2027 (no Q3 slot) | SF S&S + Data Cloud | 1.5 | Unscheduled | SF has zero Q3 headroom
SF Marketing & Analytics Operations & Enablement | P1 | H2-18 | Travel Docs (DocForge → SFMC/Web) | Q3 (Jul–Oct) | Kev / DC | 3.0 | Committed (CRM side); backend-gated | DocForge in BETA; Backend dep
SF Marketing & Analytics Operations & Enablement | P1 | H2-17 | CRM Segmentation | Q3–Q4 (Jul–Dec) | Kev / DC | 2.5 | Committed | CX briefs; pulls Data Engineer gap
SF Marketing & Analytics Operations & Enablement | P1 | H2-16 | Review Platform (TrustPilot) | Q3–Q4 (Jul–Nov) | Kev / DC | 3.5 | Committed | Platform decision; Michelle ratify
SF Marketing & Analytics Operations & Enablement | P1 | M&D | Compass CRM Reporting | Jul–Dec | Kev | 1.5 | Committed (run) | -
SF Marketing & Analytics Operations & Enablement | P1 | M&D | Voice of Customer | Jul–Sep | Kev | 1.5 | Committed | Coordinator start vs Jennifer leave
SF Marketing & Analytics Operations & Enablement | P3 | H2-07 | Marketing Consent + Double Opt-In | 2027 | Kev / SFMC (+SF S&S) | 1.5 | De-prioritised → 2027 | Cut to cap Kev at 3 FTE; SF S&S said 2027 anyway
SF Marketing & Analytics Operations & Enablement | P3 | H2-10 | Preference Centre (Web/Email) | 2027 | Kev / SFMC | 1.0 | De-prioritised → 2027 | Cut to cap Kev at 3 FTE; needs H2-07
SF Marketing & Analytics Operations & Enablement | P3 | H2-12 | AirPort Express Automation B2B | 2027 | Kev / SFMC | 1.0 | De-prioritised → 2027 | Cut to cap Kev at 3 FTE
SF Marketing & Analytics Operations & Enablement | P3 | VoC | Voice of Customer | 2027 | Kev | 0.5 | De-prioritised → 2027 | Cut to cap Kev at 3 FTE
SF Marketing & Analytics Operations & Enablement | P1 | M&D | Support / Ops | Jul–Dec | Kev | 3.0 | Committed (floor) | ~25% standing
SF Marketing & Analytics Operations & Enablement | P3 | H2-13 | SF Comms Triggers (CCE) | 2027 | Kev / SFMC | 1.5 | Deferred | After consent substrate
SF Marketing & Analytics Operations & Enablement | P3 | H2-14 | SF Data Support (mobile, DACH bug) | 2027 | Kev / SFMC | 1.0 | Deferred | -
SF Marketing & Analytics Operations & Enablement | P3 | M&D | Personalisation & Customer Insights (later phases) | 2027 | Kev / DC | TBD | Backlog | SF M&A Ops support
Booking Solutions | P1 | H2-22 | Partner API v2 | Jul–Dec (locked) | Jyhe + Lasse | 2.0/mo | Committed | Jyhe + Lasse dedicated all year
Booking Solutions | P1 | H2-21 | Bynder integration (Partner API) | Aug | Lasse | 1.0 | Committed | Lasse drops Partner API in Aug for this
Booking Solutions | P1 | H2-24 | Seaware production → OCI | Aug effort | Jonas + Øyvind | 2.0 | Committed (per grid) | OCI work in Aug; cutover window separate
Booking Solutions | P1 | H2-23 | Commercial platform / PG BAU | Jul–Dec | Darren/Erik/Halvor/Ove/Sylwester | 2.0/mo floor | Committed (ops floor) | Two green BAU lines = the ops draw
Booking Solutions | P2 | B2X | B2X Initiatives (backend support) | Aug–Dec | Sylwester | 1.0/mo | Committed (per grid) | Frontend/agent-portal backend support
Booking Solutions | P2 | SFsup | Salesforce initiative support | Sep–Dec | Erik | 1.0/mo | Committed (per grid) | Backend support to SF initiatives (ARM/API)
Booking Solutions | P2 | H2-03 | Agent-portal for top CSC flows | Jul + Sep | Erik | 1.0 | In H2 (per grid) | Now resourced — was 'needs decision'
Booking Solutions | P2 | H2-20 | Commission on Tour elements | Jul + Oct | Sylwester | 1+2 | In H2 (per grid) | Now resourced — was deferred 2027; scope still TBD
Booking Solutions | P3 | H2-05 | SFS / Fidelio stabilisation | 2027 | Jonas + Kato | 2.0 | De-prioritised → 2027 | Cut from Sep to bring Stream C within capacity
Booking Solutions | P2 | WS3 | Switzerland → DACH market migration | Aug | Darren | 1.0 | In H2 (per grid) | No as-is/to-be analysis yet
Booking Solutions | P3 | H2-06 | New payment methods (Apple/Google Pay, Vipps) | TBD | Backend | 1.0 | Not in grid — confirm | 'More or less ready'; not allocated in Jonas's grid
Booking Solutions | P3 | H2-18 | DocumentForge (backend side) | — | Backend | TBD | Not resourced (backend) | CRM side on Kev; backend not in grid
Booking Solutions | P3 | H2-04 | Automate loading & IROPS tasks | Unscheduled | Backend | 1.0 | Backlog | Not in grid

## Backlog
Customer Systems H2 2026 — Backlog (P3 / deferred / unscoped / not-planned)
Items not committed in H2. Each needs a SteerCo / lead decision before it can be scheduled.
Stream | ID | Initiative | Why not in H2 | Earliest realistic | Decision owner
SF Sales & Service Operations | H2-30 | My Account (SF identity) | SF S&S says needs Dedupe first; conflicts with Q3 pin | Q1–Q2 2027 | Sverre + Sille + Digital Products
SF Sales & Service Operations | H2-27 | Email-to-Case | Needs Dedupe complete + business resource | Q1–Q2 2027 | IT/OT + business
SF Sales & Service Operations | H2-08 | Agentforce QM pilot | Post-Lighthouse capacity; needs Connect transcripts | Q1 2027 | SF S&S + QA
SF Sales & Service Operations | M&D-135 | Case Statuses in My Account | SF capacity; needs Dedupe | 2027 | SF S&S
SF Sales & Service Operations | H2-15 | CSC Sales & Groups live reporting | Zero SF Q3 headroom | Q1 2027 | Sverre + Sille
SF Marketing & Analytics Operations & Enablement | H2-13 | SF Comms Triggers (CCE) | After consent substrate | Q1 2027 | Kev + CX
SF Marketing & Analytics Operations & Enablement | H2-14 | SF Data Support (mobile, DACH bug) | Levelled for capacity | Q2 2027 | Kev
SF Marketing & Analytics Operations & Enablement | M&D | Personalisation / Customer Insights later phases | SF M&A Ops fully loaded | 2027 | Kev + CX
SF Marketing & Analytics Operations & Enablement | — | Lighthouse 2 (from CRM view) | No CRM capacity — owned by SF S&S instead | n/a (Stream A) | Sille
SF Marketing & Analytics Operations & Enablement | — | B2B Data Ownership downstream | No CRM capacity | 2027 | Kev + Commercial
SF Marketing & Analytics Operations & Enablement | — | Commercial NorthStar Groups Ops Report | No CRM capacity | TBD | Kev + Andrew
SF Marketing & Analytics Operations & Enablement | — | Brochure Fulfilment Automation | No CRM capacity | TBD | Kev
Booking Solutions | H2-06 | New payment methods | 'More or less ready' but not allocated in Jonas's grid | Confirm | Jonas
Booking Solutions | H2-18 | DocumentForge (backend side) | Not resourced in grid; CRM side on Kev | 2027 | Jonas + Kev
Booking Solutions | H2-04 | Automate loading & IROPS tasks | Not resourced in grid | TBD | Jonas + Kato
Booking Solutions | WS4/5 | NorthStar Groups / T&Cs (business-led) | Tracked under Commercial workstreams | In flight (business) | Andrew / Karoline

## Monthly Utilisation
Customer Systems H2 2026 — Monthly Work Utilisation (FTE / month)
July = Norwegian holiday (no delivery). Plan runs Aug–Dec. Stream A re-flowed; B & C July load to be re-planned with leads. Green ≤ capacity, red = over.
Stream A — SF Sales & Service Operations (lead Sille Antonsen)
Activity | Jul | Aug | Sep | Oct | Nov | Dec
ARM (H2-11) |  | 1 | 1
Dedupe (H2-25) |  |  |  | 1 | 1.5 | 0.5
Lighthouse Ph2 (H2-09) |  | 0.8 | 0.8 | 0.9 | 0.9 | 1.4
IROPS + B2B scoping | [5 empty] | 0.5
Total utilised | 0 | 1.8 | 1.8 | 1.9 | 2.4 | 2.4
Capacity (project) | 0 | 1.8 | 2.4 | 2.4 | 2.4 | 2.4
Headroom (cap − used) | 0 | 0 | 0.6 | 0.5 | 0 | 0
Stream B — SF Marketing & Analytics Operations & Enablement (lead Kev Gaisford)
Activity | Jul | Aug | Sep | Oct | Nov | Dec
Travel Docs (H2-18) |  | 1 | 0.5 | 0.5
CRM Segmentation (H2-17) |  | 0.5 | 0.5 | 0.25 | 0.5 | 0.5
Compass CRM Reporting |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
TrustPilot (H2-16) |  | 0.75 | 0.75 | 0.75 | 0.75
ARM/Dedupe DC assist (trimmed) |  |  | 0.5 | 0.75 | 0.5
Support / Ops |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Total utilised | 0 | 3 | 3 | 3 | 2.5 | 1.25
Capacity (project) | 0 | 3 | 3 | 3 | 3 | 3
Headroom (cap − used) | 0 | 0 | 0 | 0 | 0.5 | 1.75
Stream C — Booking Solutions (lead Jonas Roineslien)
Activity | Jul | Aug | Sep | Oct | Nov | Dec
Partner API (H2-22) · Jyhe+Lasse |  | 1 | 2 | 2 | 2 | 2
Bynder (H2-21) · Lasse |  | 1
Seaware → OCI (H2-24) · Jonas+Øyvind |  | 2
Agent portal (H2-03) · Erik |  | 1 | 1
B2X Initiatives · Sylwester |  |  | 1 | 1 | 1 | 1
SF initiative support · Erik |  |  | 1 | 1 | 1 | 1
Commission (H2-20) · Sylwester |  |  |  | 1 |  | 1
Swiss market migration · Darren |  |  |  |  | 1
Total utilised | 0 | 5 | 5 | 5 | 5 | 5
Capacity (project) | 0 | 5 | 5 | 5 | 5 | 5
Headroom (cap − used) | 0 | 0 | 0 | 0 | 0 | 0

## Capacity & Streams
Stream capacity & ownership
Org team / stream | Lead (on top, excluded) | Delivery ICs | Project capacity | Position
A · Sales & Service Operations | Head of Sales & Service Ops (Sille) + Alexander Røstum (chapter) | Pawel, Nataša, Miranda, Arthur (SF Solution Specialist / Admin / Sr SF Dev roles) | 1.8 FTE Jul–Aug; 2.4 Sep–Dec | 3 commitments (ARM, Dedupe, Lighthouse Ph2); 40% BaU+OnCall floor. Holds the core SF delivery roster.
B · Marketing & Analytics Operations & Enablement | Head of Marketing & Analytics (Kev) — no direct reports in org | Kev + Guljar + Ismail | ~3.0 FTE (workload capped) | Workload capped at 3 FTE/mo; now within capacity. Consent, Preference Centre, AirPort Express and Voice of Customer de-prioritised to 2027 to fit. A dedicated Data Engineer would restore that scope.
C · Booking Solutions (incl. Platform) | Principal Eng Mgr Booking (Jonas) + Kato (chapter) — both also deliver hands-on | Jyhe, Lasse, Erik, Darren, Halvor, Ove 50%, Sylwester, Øyvind + Kirill QA (+ Jonas/Kato on OCI & SFS) | ~5.0 project FTE/mo (per Jonas grid; BaU floor 2.0 excluded) | Levelled to within capacity (at/under 5.0 every month). SFS/Fidelio de-prioritised to 2027; Swiss moved to Nov; Commission split Oct/Dec. Partner API locked (Jyhe+Lasse). Platform folded in. VAT/payments/DocForge on separate boards.
PMO · Program Coordinator | — (across all streams) | Program Coordinator (demand process, roadmap cadence) | Coordination, not delivery FTE | Owns demand intake, weekly/quarterly cadence, roadmap reporting. Sits across streams; not counted in any FTE pool.
Cross-stream conflicts to resolve: My Account timing (A: 2027 vs pinned Q3); Consent/Pref Centre (B plans Nov–Dec but needs A commitment, A says 2027); ARM ownership overlap (A vs B DC assist); SteerCo capacity expectation (only B2B scoping sits with A). See companion roadmap doc.

## Resource Allocation
Customer Systems H2 2026 — Resource Allocation by person (monthly)
Cells = primary activity (FTE). Stream A from Sille's swim-lane; Stream C partly from Jonas's canvas; Stream B + remaining C are INDICATIVE — confirm with leads.
Stream A — SF Sales & Service Operations
Person / role | Jul | Aug | Sep | Oct | Nov | Dec
Pawel · SF dev | holiday | ARM (0.6) | ARM close (0.6) | Dedupe assist (0.6) | IROPS/B2B negot. (0.6) | IROPS/B2B negot. (0.6)
Nataša · SF dev | holiday | Ph2 prep/scoping (0.6) | Ph2 prep/scoping (0.6) | Dedupe lead (0.6) | Dedupe lead (0.6) | Ph2 (0.6)
Miranda · Tech lead | holiday | ARM assist + Ph2 (0.6) | ARM close + Ph2 (0.6) | Dedupe + Ph2 (0.6) | Ph2 (0.6) | Ph2 (0.6)
Arthur · SF dev | holiday | — out (holiday) | Ph2 delivery (back) (0.6) | Ph2 delivery (0.6) | Ph2 delivery (0.6) | Ph2 delivery (0.6)
BaU + On-Call · rotated floor | holiday | 0.6 | 0.8 | 0.8 | 0.8 | 0.8
Stream B — SF Marketing & Analytics Operations & Enablement
Person / role | Jul | Aug | Sep | Oct | Nov | Dec
Guljar · Data Specialist | holiday | Seg + DC assist (1.0) | DC assist ARM/Dedupe (1.0) | DC assist (1.0) | DC assist + Seg (1.0) | Segmentation (1.0)
Ismail · Sr SFMC dev | holiday | Travel Docs + TrustPilot (1.0) | Travel Docs (0.75) | TrustPilot (0.75) | TrustPilot (0.75) | Support (0.5)
Kev · Lead (+ PO time back) | holiday | Compass + Support (0.75) | Compass + Support (0.75) | Compass + Support (0.75) | Compass + Support (0.75) | Compass + Support (0.75)
De-prioritised → 2027 · Consent · Pref Centre · AirPort · VoC | holiday | — | — | — | — | —
Stream C — Booking Solutions
Person / role | Jul | Aug | Sep | Oct | Nov | Dec
Jyhe · Partner API · Sr Backend · LOCKED | holiday | 1.0 | 1.0 | 1.0 | 1.0 | 1.0
Lasse · Partner API / Bynder · Backend · LOCKED | holiday | Bynder 1.0 | 1.0 | 1.0 | 1.0 | 1.0
Jonas · Seaware OCI · Platform lead (hands-on) | holiday | OCI 1.0 | — | — | — | —
Øyvind · Seaware OCI · Backend / Infra | holiday | OCI 1.0 | — | — | — | —
Erik · Agent portal / SF support · Sr Backend | holiday | Agent portal 1.0 | Agent portal 1.0 | SF support 1.0 | SF support 1.0 | SF support 1.0
Darren · Swiss migration · Sr Backend | holiday | — | — | — | Swiss 1.0 | —
Sylwester · Commission / B2X · Backend | holiday | B2X 1.0 | B2X 1.0 | Commission 1.0 + B2X 1.0 | B2X 1.0 | Commission 1.0 + B2X 1.0
Halvor / Ove (50%) · Sr Backend | holiday | BaU / platform | BaU / platform | BaU / platform | BaU / platform | BaU / platform
Kirill · QA · Test Specialist | holiday | Test across | Test across | Test across | Test across | Test across
Platform + PG/Platform BAU · ops floor (green) | holiday | 2.0 | 2.0 | 2.0 | 2.0 | 2.0
De-prioritised → 2027 · SFS / Fidelio (was Sep) | holiday | — | — | — | — | —
Net capacity (levelled) · spare(+) / over(−) | holiday | 0 | 0 | 0 | 0 | 0